## Sheet1
Path 1 |  | Path 2
Requirements Gathering | 3 days | Requirements Gathering | 3 days
UI/UX Design | 4 days | Backend Setup | 3 days
API Integration | 3 days | Frontend Development | 5 days
Testing | 4 days | Testing | 4 days
Review & Feedback | 2 days | Review & Feedback | 2 days
TOTAL DAYS: | 16 days | TOTAL DAYS: | 17 days
Critical Path | Path 2
*Path that takes the longest